## Stories
Sprint | Who | Story | Estimate | Actual Time Spent
1 |  | 2017-06-09
|  | Prototype Python web app backend | 1 | 1
|  | Initial server and domain name setup | 2 | 1
|  | Create front-end foundations | 5 | 8
|  | Choose pre-supplied songs | 1 | 1
|  |  | Slack: | -2
2 |  | 2017-06-30
|  | Prototype genre recognition neural network | 21
|  | Design UI | 3
|  | Implement song upload option | 5
|  | Implement youtube link option | 5
|  | Implement spectrogram generation | 8
|  | Implement music metadata extraction | 8
3 |  | 2017-07-21
|  | Move UI design to code | 5
|  | Prototype image generator neural network | 21
|  | Implement music visualization | 8
|  | Implement user approval/disapproval | 5
|  | Implement logging for training purposes | 8
Release July 21
|  | Total | 106
|  | Completed | 9
|  | Remaining | 97
|  | % Complete | 8.491%
|  | Avg Velocity | 1.8
|  | Estimated # Iterations Remaining | 53.8889
Parking Lot
|  | Nice to have story #1 | 3
|  | Nice to have story #2 | 5
Dropped
|  | Stuff we didn't need #1 | 6
Stuff we didn't need #2

## Sprint Data
| 2017-06-09 | 2017-06-30 | 2017-07-21
| 1 | 2 | 3
Total Effort | 53 | 53 | 53
Velocity | 0 | 0 | 0
Remaining | 53 | 53 | 53
Completed | 0 | 0 | 0
% complete | 0% | 0% | 0%